## Flood Mit Improvement Prog
Project number & description | Status 2025 | Notes
1.a) Implement debris control measures for Federation Bridge | Complete | In 2023, the Federation Bridge Debris Control Stage 1 – Options Assessment report was completed. This report identified Camphor Laurel management and bush regeneration.
1.b) Implement debris control measures for the Billinudgel Railway Bridge. | In Progress | Project commenced and draft report received from engaged consultant - draft report presented to October 2025 Flood Advisory Committee.
2. Further investigate raising eligible residential properties to reduce flood damage. | Re-assigned | Proposed as part of the VHR/VHP scheme, taken over by the NSW Reconstruction Authority
3. Preferred Byron Drainage Strategy Construction. | In Progress | Grant awarded for design phase only. Contract award by August 23. Construction planned for May-November 2025
4. Develop a whole-of-catchment drainage model and overland flow path investigation. | In Progress | Grant Application Successful, Tendered & Contract Awarded. Draft modelling results presented to August 2025 Flood Advisory Committee. Project completion date expected 12/12/2025
5. Undertake a more detailed assessment of properties that may benefit from property-level protection. | In Progress | Will form part of the scope of the Shire overland flow path study
6. Voluntary House Raising Scheme. | Re-assigned | The grant was submitted on May 22 for 2/3 funding for up to 2 houses. The Total Scheme is 57 houses at $150K per house. The project was taken over by the NSW Reconstruction Authority
7. Implement the recommendations of the South Golden Beach levee audit. | Re-assigned | Funding awarded, Program to be delivered by NSW Public Works Dept - expect commencement May 2025
8. Upgrade the Broken Head Road Crossing of South Tallow Creek. | In Progress | Detailed design report and cost-estimates received and supplied. REF constraints report to be received October 2025. Project delayed - earliest time of completion December 2025.
9. Upgrade Coogera Circuit Detention. | Complete | Project completed 30/6/2025
10. Drainage Infrastructure Maintenance. | Complete | Completed post 2022 flood - One-off clean of main drains in Byron Bay
11. Further detailed assessment of Saltwater Creek upgrade assessment and mitigation options for Mullumbimby. (incl. Influence of structures) | Not Started | Will form part of the scope of the North Byron Flood Study (i.e. 2025 Brunswick River Catchment Flood Study), Risk Study, and Plan Updates
12. Undertake an Evacuation Assessment for Mullumbimby. | In Progress | This project has been postponed following meeting discussions with SES and NSW RA in September 2025.
13. Identify key roads and implement automatic warning signs and depth indicators. | Complete | Grant Application Successful - 3 Auto Flood Signs installed at Myocum, Main Arm and Mullumbimby
14. Community Flood Awareness. | Complete | Part of the Tallow / Belongil Creek Flood Risk Management Studies and Plans
15. Consider establishing a Voluntary House Purchase scheme for eligible properties. | Not Started | Will form part of the scope of the North Byron Flood Study, Risk Study, and Plan Updates. Noting: The North Byron Flood Study will be called the Brunswick River Catchment Flood Study to be more fitting to the geographic area and contributing catchment.
16. More detailed assessment of the potential raising of River Street to provide improved flood immunity and evacuation. | Not Started | Will form part of the scope of the North Byron Flood Study, Risk Study, and Plan Updates. Noting: The North Byron Flood Study will be called the Brunswick River Catchment Flood Study to be more fitting to the geographic area and contributing catchment.
17. Further consider viable options to implement the recommendations of the New City Road drainage assessment. | Not Started | Not explicitly included in the Byron Shire Council Overland Flow Path Study scope, to be addressed in the Brunswick River Catchment FRMSP (Flood Risk Management Study and Plan).
18. New Byron Local Environment Plan to more robustly protect existing development from increased flooding impacts resulting from future development, and update to be in line with the NSW Floodplain Development Manual (2005). | Complete | Captured in LEP clauses 5.21 and 5.22
19. SGB Flood Pump Generator. | Complete | Generator installed and operational
20. Investigate Options for SGB Flood Gate Upgrades. | Complete | Design and manufacturing complete. Installation complete. Grates installed 2025
21. Investigate SGB and Fern Beach Flood Levy Upgrades. | Complete | Levy overtopped in 2022. Propose to raise the Levy. A feasibility assessment by NSW Public Works found that raising the levee by 300mm or 600mm is not plausible. Additionally, Report Supplied as attachment in August 2025 Flood Advisory Committee.
22. Investigate the Flood pump for the Western SGB levee. | Complete | Report prepared and submitted to Flood Advisory Committee, August 21st 2025
23. Post-Event Shire-wide Flood Planning Level Review. | In Progress | Proposed action following the post-event report
24. Council and the SES to update the Local Flood Plan based on findings of the FRMS. | Re-assigned | Underway with the SES. Flood GIS data for varying AEP's (flood design events) supplied into SES portal (September 2025). Data also needed from Brunswick River Catchment Flood Study.
25. Engage with the community to prepare an ongoing flood education program, with appropriate evaluation by Council and SES following implementation. | Not Started | Funding to be sought. This will form part of the scope of the Brunswick River Catchment Flood Study, Risk Study and Plan Updates
26. Further consideration of Avocado Court drainage modification. | Re-assigned | Will form part of the scope of Shire overland flow path study & updated Brunswick River Catchment Flood Study, Risk Study and Plan Updates
27. Develop a sediment transport model to investigate modifications to the rock walls, as part of the Coastal Management Program for the Brunswick Estuary. | Unfunded | -
28. Further consideration of Billinudgel infrastructure improvements. | Not Started | Will form part of the scope of the Brunswick River Catchment Flood Study, Risk Study, and Plan Updates, as well as the Shire overland flow path study
29. Develop guidance on the design and installation of fencing traversing waterways and channels. | Complete | Will form part of the scope of the Brunswick River Catchment Flood Study, Risk Study, and Plan Updates, as well as the Belongil and Tallow equivalents
30. Flood Planning Levels revised based on the recommendations of the FRMS. | In Progress | Will form part of the scope of the Brunswick River Catchment Flood Study, Risk Study, and Plan Updates
31. Section 10.7 (5) certificates to provide further detail of flood behaviour. Consideration to providing property-level flood information via an online GIS platform. | Complete | Online system available
32. Byron Shire Council and SES to consider the findings and recommendations of the FRMS in the development of the Flood Warning Network for North Byron. | Complete | New Gauges and IMS systems
33. Changes to land use zoning should consider flood compatibility based on the recommendations of the FRMS. | Complete | Will form part of the scope of the Brunswick River Catchment Flood Study, Risk Study, and Plan Updates
34. Form a committee, comprising council, state, emergency services and community member representatives, to oversee the implementation of the FRMP. | Complete | Flood Advisory Committee established
35. Commence undertaking to rezone the land identified as high flood hazard for the 1 in 100-year ARI flood to preclude these areas from future development. | Deleted - Hazard areas established | No specific hazard zone exists in the Standard Instrument LEP. Nearly all high flood hazard land is zoned rural or environmental
36. Adopt FPLS as part of the DCP 2002, to the extent of flood-prone land in the Tallow Creek catchment, considering climate change conditions (Scenario 4). | Complete | Undertaken immediately following the 2015 FRMSP
37. Adopt prescribed areas of fill exclusion. | Complete
38. Ensure future developments within the catchment utilise on-site stormwater detention measures to maintain predevelopment peak runoff characteristics. | Complete | This is part of Council's Development Control Plan
39. Update 149 certificates and any lots with additional controls over them, including add 1495 certificates for lots effected by PMF and not within the FPL. | Complete | Undertaken in 2021 in accordance with Planning Circular PS 21-006
40. Adopt a new version of the hydraulic model to allow for the assessment of all proposed development. | In Progress | Will be an output of the Tallow Creek Flood Risk Management Study & Plan
41. Establish a relationship between the flood return period, sand bar levels and flooding conditions in Tallow Lake to assist in SES flood evacuation planning. | In Progress | Will be an output of the Tallow Creek Flood Risk Management Study & Plan
42. Install a flood gauge at the Broken Head Road culvert showing example flood levels. | Not Started | Project removed from priority list due to lack of severe flooding at the proposed site.
43. Install a lake level and rainfall monitoring station on Tallow Lake and connect to the Council’s flood warning system. | Complete | Tallow Creek ALERT installed. Also repositioned in September 2025 due to footbridge renewals.
44. Raise footpath at Tallow Lake footbridge to ensure trafficable up to a lake level of 2.5mAHD | Complete | Not funded
45. Develop and implement asset management and maintenance plan. | Complete
46. Implement an interim management plan through water level and quality monitoring. | Complete/Ongoing | Action is from the Tallow Creek Floodplain Risk Management Study and Plan (SKM 2015). This action is complete insofar as it relates to the action outlined in the plan. Council continues to monitor lake levels as part of our operational BAU. Water quality monitoring pre, during and post entrance management is undertaken in association with our quite prescriptive licence conditions
47. Develop data collection program for variables such as sand bar and lake stored level, to support development of long-term management plan. | In Progress | Ongoing with Coastal Management Team
48. Inspect the sand bar and record its level every year prior to the onset of the rainfall season. | In Progress | Ongoing with Coastal Management Team
49. Monitor the level of the opening during the rainfall season and undertake maintenance earthworks to restore the level as per the accepted Interim Sandbar Management Strategy. | In Progress | Ongoing with Coastal Management Team
50. Update Council Geographic Information Systems (GIS) to include outputs of this plan and update any lots with additional controls over them. | Complete | Updated.
51. Ensure Authority uses the GIS layers to prepare property reports. | Complete
52. Add adopted document to Council’s website, plus additional A1 PDF of FPL. | Complete
53. Preferred Byron Drainage Strategy Design | Complete
54. Development Controls. | Complete
55. Emergency Planning (SMS Messaging). | Complete | Implemented as part of flood warning network and emergency dashboard
56. Flood Information Dataset. | Complete | Implemented as part of flood warning network and emergency dashboard
57. Belongil Creek Entrance Strategy. | Complete | EOS undergoes biennial reviews that evaluate the breach trigger level in light of new flood studies and sea level rise data. Longer-term management options for the Belongil catchment are being considered through the Coastal Management Program (CMP), with public consultation expected soon
58. Flood Gauges. Install six new gauges in collaboration with BoM | In Progress | On hold whilst BoM (Bureau of Meteorology) transition/uplift ALERT station network. ALERT stations installed, awaiting new device IDs with BoM.
59. Revise the Flood Planning Area based on the recommendations of the FRMS. | Complete | Completed in 2020.
60. Council consider updating the DCP to incorporate the recommendations detailed in the FRMS; | In Progress
61. Byron Shire Council compliance team investigate illegal builds south of North Heads Road. | In Progress
62. Implementation of design measures and evacuation plans to minimise impacts on future planned community uses as identified in the DCP No. 9 | In Progress
63. Prepare a section contribution plan for all civil works in this plan. | Complete | Not Supported by Council
64. Support SES in the inclusion of Suffolk Park in the Flood Response Plan. | Complete