## Capital Works Program 4 years
Project details and location | Category | Status | Total cost | Year
Bangalow Road - Safer Roads Program - Talofa | ROADS | Construction Underway | 1985672 | 2021/22
Coolamon Scenic Drive - Safer Roads Program | ROADS | Design Underway | 2432184 | 2021/22
The Pocket Road Stage 2 Renewal - The Pocket | ROADS | Design Underway | 1300000 | 2021/22
Repentance Creek Road Causeway Replacement - Goonengerry | BRIDGES / CAUSEWAYS | Complete | 7109000 | 2021/22
Ewingsdale Road Shared Path Missing Link Upgrade - Byron Bay | CYCLEWAY / SHARED PATH / FOOTPATH | Construction Planned | 176603 | 2021/22
44 Kingsley Lane - Kerb and Gutter - Byron Bay | STORMWATER | Construction Planned | 176100 | 2021/22
18 Old Bangalow Road - Pipe to reserve - Byron Bay | STORMWATER | Project On Hold | 120000 | 2021/22
Pacific Esplanade Street Drainage Upgrade - South Golden Beach | STORMWATER | Construction Underway | 195000 | 2021/22
30/32 Rajah Road Overland Flow Path - Ocean Shores | STORMWATER | Construction Planned | 85000 | 2021/22
Studal Lane Drainage Upgrade - Mullumbimby | STORMWATER | Project Planned | 25000 | 2021/22
Myocum Road Safety Improvements and Reconstructions (Including Fixing Country Roads project) | ROADS | Construction Underway | 7364708 | 2021/22
Integrated Transport Management Strategy - Shire Wide | TRANSPORT | Project Underway | 175000 | 2021/22
Tallow Creek Footbridge - Approach Path Raising - Suffolk Park | BRIDGES / CAUSEWAYS | Construction Planned | 60000 | 2021/22
Brunswick Heads - Parking Scheme Review | TRANSPORT | Construction TBC | 0 | 2021/22
Rifle Range Road Intersection Upgrade - Bangalow | ROADS | Design Underway | 2089075 | 2021/22
Johnston's Lane Causeway Upgrade - Main Arm | BRIDGES / CAUSEWAYS | Project Planned | 250203 | 2021/22
Kolora Way Shared Path - Stage 2 - South Golden Beach | CYCLEWAY / SHARED PATH / FOOTPATH | Project Underway | 160000 | 2021/22
South Beach Road and Car Park Upgrade - Brunswick Heads | ROADS | Design Underway | 945000 | 2021/22
Broken Head Road On Road Cycleway - Stage 2 - Suffolk Park to Byron Bay | CYCLEWAY / SHARED PATH / FOOTPATH | Construction Underway | 2570000 | 2021/22
Lawson Street from Fletcher to Middleton - Road Renewal - Byron Bay | ROADS | Design Underway | 600000 | 2021/22
Bayshore Drive - Road Renewal and Shared Path - Byron Arts and Industrial Estate, Byron Bay | ROADS | Project Underway | 1700000 | 2021/22
Stuart Street Renewal and Green Spine - Mullumbimby | ROADS | Design Underway | 1287600 | 2021/22
Carlyle Street - Road Renewal - Byron Bay | CYCLEWAY / SHARED PATH / FOOTPATH | Design Underway | 1130000 | 2021/22
Main Arm Road Road Safety Improvements and Reconstructions - Rural | ROADS | Design Underway | 5050000 | 2021/22
Tincogan Street Intersection Priority Changes - Mullumbimby | ROADS | Design Underway | 341155.86 | 2021/22
Fern Street Renewal - Station St to Dalley St - Mullumbimby | ROADS | Design Underway | 724500 | 2021/22
Lighthouse Road / Clarkes Beach Reflections Stormwater Diversion - Byron Bay | STORMWATER | Construction Planned | 1460000 | 2021/22
Minyon Falls Road Upgrade - Repentance Creek | ROADS | Design Underway | 473742 | 2021/22
Grays Lane - Road Upgrade - Tyagarah | ROADS | Design Complete | 833833 | 2021/22
Deacon Street - Shared Path - Bangalow | CYCLEWAY / SHARED PATH / FOOTPATH | Design Complete | 425000 | 2021/22
Clifford Street - Road and Drainage Upgrade - South Golden Beach | STORMWATER | Design Underway | 145000 | 2021/22
Seven Mile Beach Road - Road Upgrade and Parking Improvements - Broken Head | ROADS | Design Underway | 362000 | 2021/22
Broken Head Reserve Road and Village - Improvements - Broken Head | ROADS | Design Underway | 277000 | 2021/22
Keyes Bridge Parking Improvements - Rural | ROADS | Project Planned | 5000 | 2021/22
Skinners Shoot Road - Road Safety Improvements - Skinners Shoot | ROADS | Complete | 510000 | 2021/22
Balemo Drive - Shared Path - Ocean Shores | CYCLEWAY / SHARED PATH / FOOTPATH | Complete | 927707 | 2021/22
Englishes Road - Bridge Replacement - Upper Coopers Creek | BRIDGES / CAUSEWAYS | Design Underway | 671159 | 2021/22
Main Arm Road - Bridge Replacement - Upper Main Arm | BRIDGES / CAUSEWAYS | Design Underway | 396518.51 | 2021/22
Sherringtons Lane - Bridge Replacement - The Pocket | BRIDGES / CAUSEWAYS | Project Planned | 502287.4 | 2021/22
Main Arm Road #02 - Causeway Renewal - Main Arm | BRIDGES / CAUSEWAYS | Design Underway | 800000 | 2021/22
Tennyson Street - Shared Path - Byron Bay | CYCLEWAY / SHARED PATH / FOOTPATH | Construction Planned | 951818 | 2021/22
Byron Street - Shared Path - Bangalow | CYCLEWAY / SHARED PATH / FOOTPATH | Design Underway | 100000 | 2021/22
Mullumbimby to Brunswick Heads - New On Road Cycleway - Mullumbimby | CYCLEWAY / SHARED PATH / FOOTPATH | Project Underway | 520000 | 2021/22
Radar Activated Speed Sign Trial - Shire Wide | TRANSPORT | Project Underway | 50000 | 2021/22
Fixing Local Roads Renewal - Ocean Shores | ROADS | Project Underway | 3000000 | 2021/22
Bus Stop Accessibility Upgrade Program - Shire Wide | TRANSPORT | Project Planned | 500000 | 2021/22
Station Street - Road and Drainage Upgrade - Mullumbimby | STORMWATER | Design Underway | 490000 | 2021/22
Helen Street Footbridge Deck Renewal Stage 1 | BRIDGES / CAUSEWAYS | Programmed | 100000 | 2022/23
Urban Laneway Drainage Master Planning Program | ROADS | Programmed | 60000 | 2022/23
SGB Street Drainage Upgrade - Gloria Street (east) - Construction | STORMWATER | Programmed | 260000 | 2022/23
SGB Street Drainage Upgrade - Royal Ave & Gloria (west) - Design | STORMWATER | Programmed | 25000 | 2022/23
Rehabilitate Bangalow Wetland | STORMWATER | Programmed | 50000 | 2022/23
Investigate bank erosion and protect assets adj Childe Street/Manfred St | ROADS | Programmed | 30000 | 2022/23
Seven Mile Beach Road Traffic Control Works Stage 2 | ROADS | Programmed | 160000 | 2022/23
Bus Stop Accessibility Upgrade Program | TRANSPORT | Programmed | 300000 | 2022/23
Main Arm Road | ROADS | Programmed | 1058109 | 2022/23
Station Street | ROADS | Programmed | 669000 | 2022/23
Byron Bay Town Centre Masterplan Projects to be determined | PLACE PLANNING | Programmed | 500000 | 2022/23
Major Patching Program - Impacts of Tourism Fund | ROADS | Programmed | 600000 | 2022/23
Annual Reseal capital renewal Program - Shire Wide | ROADS | Programmed | 650000 | 2022/23
Lawson Street Renewal - Jonson to Fletcher - Byron Bay - Construction | ROADS | Programmed | 550000 | 2022/23
Kingsley Street Renewal - Byron Bay - Construction | ROADS | Programmed | 800000 | 2022/23
Carlyle Street Renewal - Section 2 - Byron Bay - Construction | ROADS | Programmed | 450000 | 2022/23
Main Arm Road Renewal - Construction Stage 2 | ROADS | Programmed | 600000 | 2022/23
Bayshore Drive Renewal - Byron Arts and Industrial Estate - Byron Bay - Construction Stage 2 | ROADS | Programmed | 800000 | 2022/23
Redgate & New Brighton Road Footpath Reseal | CYCLEWAY / SHARED PATH / FOOTPATH | Programmed | 100000 | 2022/23
Marshalls Creek Foreshore & Roadside Erosion Improvements - New Brighton - Construction | ROADS | Programmed | 240000 | 2022/23
Annual capital gravel resheeting program - Shire Wide | ROADS | Programmed | 360000 | 2022/23
Annual bridge capital renewal program - Shire Wide | BRIDGES / CAUSEWAYS | Programmed | 100000 | 2022/23
Causeway Capital Maintenance Works Program | BRIDGES / CAUSEWAYS | Programmed | 50000 | 2022/23
Major Culverts Capital Maintenance Works Program | BRIDGES / CAUSEWAYS | Programmed | 40000 | 2022/23
Annual Major Patching capital renewal Program - Shire Wide | ROADS | Programmed | 520000 | 2022/23
Annual Asphalt Overlay capital renewal Program - Shire Wide | ROADS | Programmed | 800000 | 2022/23
Annual Reseal capital renewal Program - Shire Wide | ROADS | Programmed | 1705850 | 2022/23
Annual Road Side Barrier Capital Renewal Program - Shire Wide | ROADS | Programmed | 200000 | 2022/23
Annual access ramp and footpath upgrade and renewal program - Shire Wide | CYCLEWAY / SHARED PATH / FOOTPATH | Programmed | 74000 | 2022/23
Annual Retaining Wall capital renewal Program - Shire Wide | ROADS | Programmed |  | 2022/23
Annual stormwater capital renewal program - Shire Wide | STORMWATER | Programmed |  | 2022/23
Annual Footpath capital renewal program - Shire Wide | CYCLEWAY / SHARED PATH / FOOTPATH | Programmed | 107500 | 2022/23
Annual Kerb and Gutter capital renewal program - Shire Wide | ROADS | Programmed | 44000 | 2022/23
Urban Laneway Drainage Master Planning Program | ROADS | Programmed | 60000 | 2023/24
Studal Lane Drainage Upgrade - Construction | STORMWATER | Programmed | 200000 | 2023/24
Fingal Lane - resolve flooding issues from lane developments - Design | STORMWATER | Programmed | 25000 | 2023/24
Gaggin Street New Brighton - resolve property flooding poor subdivision driveway designs - Design | STORMWATER | Programmed | 25000 | 2023/24
SGB Street Drainage Upgrade - Royal Ave & Gloria (west) - Construction | STORMWATER | Programmed | 230000 | 2023/24
Urban Main Renewal / Realign Program - Langi Place replace pipes between D000012132 and D000012132 | STORMWATER | Programmed | 120000 | 2023/24
Urban Main Renewal / Realign Program - Matong Drive replace pipes between pits D000011322 and D00001321 | STORMWATER | Programmed | 120000 | 2023/24
Urban Main Renewal / Realign Program - Construct Parcel 54790 Ocean Shores | STORMWATER | Programmed | 200000 | 2023/24
Bus Stop Accessibility Upgrade Program | TRANSPORT | Programmed | 500000 | 2023/24
New Brighton Road | ROADS | Programmed | 110000 | 2023/24
Peter Street | ROADS | Programmed | 155000 | 2023/24
Robin Street | ROADS | Programmed | 155000 | 2023/24
Phillip Street | ROADS | Programmed | 155000 | 2023/24
Fingal Street - DESIGN | ROADS | Programmed | 40000 | 2023/24
Grevillea Street - DESIGN | ROADS | Programmed | 50000 | 2023/24
Banksia Drive - DESIGN | ROADS | Programmed | 110000 | 2023/24
Alcorn Street - DESIGN | ROADS | Programmed | 20000 | 2023/24
Carlyle Street - DESIGN | ROADS | Programmed | 45000 | 2023/24
Gloria Street - DESIGN | ROADS | Programmed | 20000 | 2023/24
Royale Avenue - DESIGN | ROADS | Programmed | 20000 | 2023/24
Byron Bay Town Centre Masterplan Projects to be determined | PLACE PLANNING | Programmed | 500000 | 2023/24
Annual capital gravel resheeting program - Shire Wide | ROADS | Programmed | 365000 | 2023/24
Annual bridge capital renewal program - Shire Wide | BRIDGES / CAUSEWAYS | Programmed | 150000 | 2023/24
Causeway Capital Maintenance Works Program | BRIDGES / CAUSEWAYS | Programmed | 50000 | 2023/24
Major Culverts Capital Maintenance Works Program | BRIDGES / CAUSEWAYS | Programmed | 50000 | 2023/24
Annual Major Patching capital renewal Program - Shire Wide | ROADS | Programmed | 540000 | 2023/24
Annual Asphalt Overlay capital renewal Program - Shire Wide | ROADS | Programmed |  | 2023/24
Annual Reseal capital renewal Program - Shire Wide | ROADS | Programmed | 1694200 | 2023/24
Annual Road Side Barrier Capital Renewal Program - Shire Wide | ROADS | Programmed | 200000 | 2023/24
Annual access ramp and footpath upgrade and renewal program - Shire Wide | CYCLEWAY / SHARED PATH / FOOTPATH | Programmed | 76000 | 2023/24
Annual Retaining Wall capital renewal Program - Shire Wide | ROADS | Programmed |  | 2023/24
Annual stormwater capital renewal program - Shire Wide | STORMWATER | Programmed |  | 2023/24
Annual Footpath capital renewal program - Shire Wide | CYCLEWAY / SHARED PATH / FOOTPATH | Programmed | 110700 | 2023/24
Annual Kerb and Gutter capital renewal program - Shire Wide | ROADS | Programmed | 44000 | 2023/24
Tallow Creek Footbridge Renewal | BRIDGES / CAUSEWAYS | Programmed | 500000 | 2024/25
Urban Laneway Drainage Master Planning Program | STORMWATER | Programmed | 60000 | 2024/25
Alcorn Street Drainage Augmentation - Construction | STORMWATER | Programmed | 220000 | 2024/25
SGB Street Drainage - Rear easements Augmentation East side - Planning | STORMWATER | Programmed | 30000 | 2024/25
SGB Street Drainage Stage - Rear easements Augmentation West side - Planning | STORMWATER | Programmed | 30000 | 2024/25
Belongil Voluntary House Raising (1:2 grant) | FLOOD | Programmed | 60000 | 2024/25
Design Avocado / Grevillea Overland Flow Path | STORMWATER | Programmed | 30000 | 2024/25
Bangalow Flood Study | FLOOD | Programmed | 103000 | 2024/25
Mullumbimby Gulgan RAB - concept design & investigations | ROADS | Programmed | 50000 | 2024/25
Scarrabelottis Lookout - temp parking and access control (Res 18-159) | ROADS | Programmed | 20000 | 2024/25
Byron Bay Town Centre Masterplan Projects to be determined | PLACE PLANNING | Programmed | 500000 | 2024/25
Annual capital gravel resheeting program - Shire Wide | ROADS | Programmed | 370000 | 2024/25
Annual bridge capital renewal program - Shire Wide | BRIDGES / CAUSEWAYS | Programmed | 150000 | 2024/25
Causeway Capital Maintenance Works Program | BRIDGES / CAUSEWAYS | Programmed | 400000 | 2024/25
Major Culverts Capital Maintenance Works Program | BRIDGES / CAUSEWAYS | Programmed | 50000 | 2024/25
Annual Major Patching capital renewal Program - Shire Wide | ROADS | Programmed |  | 2024/25
Annual Asphalt Overlay capital renewal Program - Shire Wide | ROADS | Programmed | 800000 | 2024/25
Annual Reseal capital renewal Program - Shire Wide | ROADS | Programmed | 1741475 | 2024/25
Annual Road Side Barrier Capital Renewal Program - Shire Wide | ROADS | Programmed | 200000 | 2024/25
Annual access ramp and footpath upgrade and renewal program - Shire Wide | CYCLEWAY / SHARED PATH / FOOTPATH | Programmed | 80800 | 2024/25
Annual Retaining Wall capital renewal Program - Shire Wide | ROADS | Programmed |  | 2024/25
Annual stormwater capital renewal program - Shire Wide | STORMWATER | Programmed |  | 2024/25
Annual Footpath capital renewal program - Shire Wide | CYCLEWAY / SHARED PATH / FOOTPATH | Programmed | 116200 | 2024/25
Annual Kerb and Gutter capital renewal program - Shire Wide | ROADS | Programmed | 35500 | 2024/25

## Roadside Barrier Program 1 year
Serial Number | Location | Type | Status | Cost | Year
1 | Tweed Valley Way | Guard rail | Construction Planned | 25000 | 2021/22
2 | Brunswick Valley Way | Guard rail | Construction Planned | 20000 | 2021/22
3 | Wilsons Creek Rd | Brifen Fence | Construction Planned | 20000 | 2021/22
4 | Byron St, Bangalow | Guard rail | Construction Planned | 20000 | 2021/22

## Grading Program 1 year
Serial Number | Location | Status | Cost | Year
1 | Robinsons Lane | Completed | Column2 | 2021/22
1 | Robinsons Lane | Complete | 5803 | 2021/22
2 | Koonyum Range Rd, Wilson Creek | Complete | 16968 | 2021/22
3 | Wilsons Creek Rd | Complete | 32550 | 2021/22
4 | Gittoes Ln, Possum Creek | Complete | 6020 | 2021/22
5 | Wanganui Rd, Wanganui | Complete | 21420 | 2021/22
6 | Huonbrook Rd | Complete | 45990 | 2021/22
7 | Sheaffs Rd, Federal | Complete | 10570 | 2021/22
8 | Jarretts Rd | Complete | 2520 | 2021/22
9 | Beatties Ck Rd | Complete | 2009 | 2021/22
10 | Bates Rd, Federal | Complete | 6790 | 2021/22
11 | Yankee Ck Rd | Complete | 9639 | 2021/22
12 | Grays Ln, Tyagarah | Project Planned | 6020 | 2021/22
13 | Walkers Ln, The Pocket | Project Planned | 5670 | 2021/22
14 | Riley Lane, Mullumbimby | Project Planned | 2660 | 2021/22
15 | Tennyson St, Byron Bay | Project Planned | 4879 | 2021/22
16 | McGregor St, Suffolk Park | Project Planned | 2870 | 2021/22
17 | Shirley Lane, Byron Bay | Project Planned | 4074 | 2021/22
18 | Pacific Espalande | Project Planned | 2618 | 2021/22
20 | Upper Coopers Creek Rd | Project Planned | 19278 | 2021/22
21 | Snow Ck Rd | Project Planned | 595 | 2021/22
22 | Tickles Rd | Project Planned | 3402 | 2021/22
24 | Englishes Rd | Project Planned | 1260 | 2021/22
25 | Rosewood Rd, Federal | Project Planned | 3920 | 2021/22
26 | St Helenas Rd, McLeods Shoot | Project Planned | 19138 | 2021/22
27 | Piccadilly Hill Rd | Project Planned | 20832 | 2021/22
28 | Coopers Lane West, Main Arm | Project Planned | 13510 | 2021/22
29 | Shirley Lane, Byron Bay | Project Planned | 4074 | 2021/22
30 | Manfred St, Belongil | Project Planned | 385 | 2021/22
33 | Dingo Lane, Myocum | Project Planned | 18340 | 2021/22
35 | Burnetts Rd, Nashua | Project Planned | 9940 | 2021/22
36 | Scarrabelottis Rd, Nashua | Project Planned | 8610 | 2021/22
37 | 7 Mile Beach Rd | Project Planned | 16660 | 2021/22
38 | Jones Rd, Yelgun | Project Planned | 14910 | 2021/22
40 | Byron Creek Rd | Project Planned | 2345 | 2021/22
42 | Tims Lane, Broken Head | Project Planned | 7000 | 2021/22
43 | Willows Rd, Billinudgel | Project Planned | 3325 | 2021/22
44 | Wilfred St, Billinudgel | Project Planned | 1890 | 2021/22
45 | Kings Rd | Project Planned | 15470 | 2021/22
46 | South Beach Lane, Brunswick Heads | Project Planned | 1652 | 2021/22
47 | Waltons Rd, Federal | Project Planned | 12880 | 2021/22
48 | Blindmouth Rd, Main Arm | Project Planned | 17080 | 2021/22
49 | The Esplanade, New Brighton | Project Planned | 2254 | 2021/22
50 | Saddle Rd | Project Planned | 13300 | 2021/22
53 | Lawlers Lane | Project Planned | 6685 | 2021/22
56 | McPhails Rd | Project Planned | 4130 | 2021/22
57 | Taylors Rd, Nashua | Project Planned | 3885 | 2021/22
60 | Kennedys Lane | Project Planned | 9660 | 2021/22
62 | Charltons Rd | Project Planned | 12740 | 2021/22
63 | Goonengerry Mill Rd | Project Planned | 13370 | 2021/22
64 | Middle Pocket Rd, Middle Pocket | Project Planned | 2240 | 2021/22
65 | Coral Ave, Mullumbimby | Project Planned | 2905 | 2021/22
66 | Clay Rd, Mullumbimby | Project Planned | 8680 | 2021/22
67 | Lomandra Lane, Mullumbimby | Project Planned | 2415 | 2021/22
69 | Billinudgel Rd | Project Planned | 12600 | 2021/22
70 | Chinamans Hill Rd | Project Planned | 3395 | 2021/22
73 | North Head Rd | Project Planned | 2730 | 2021/22
74 | Riversea Lane, New Brighton | Project Planned | 1309 | 2021/22
78 | Synotts Lane, Ocean Shores | Project Planned | 2800 | 2021/22
80 | Settlement Rd, Main Arm | Project Planned | 13370 | 2021/22
81 | Dudgeons Rd | Project Planned | 4060 | 2021/22
82 | Cedarvale Rd | Project Planned | 1540 | 2021/22
84 | Flowers Ln, Bangalow | Project Planned | 8960 | 2021/22
86 | Rifle Range Rd | Project Planned | 700 | 2021/22
89 | Newell Rd | Project Planned | 1365 | 2021/22
90 | Motts Rd, Upper Main Arm | Project Planned | 8190 | 2021/22
92 | Tooheys Mill Rd | Project Planned | 14224 | 2021/22
93 | Coopers Ln, Main Arm | Project Planned | 13510 | 2021/22
94 | Johnstons Lane | Project Planned | 1540 | 2021/22

## Asphalt Overlay Program 1 year
Street Name | Status | Date Completed | Chainage From | Chainage To | Length (m) | Cost | Year
MORRISON AVE | Complete | 2021-07-08 | 10 | 260 | 250 | 80241.82 | 2021/22
CENOTAPH LANE | Complete | 2021-07-16 | 5 | 105 | 100 | 38116.46 | 2021/22
PALM AVE | Complete | 2021-07-29 | 0 | 170 | 170 | 54673.27 | 2021/22
ALDINGA COURT | Project Planned |  | 0 | 104 | 104.2 | 30000 | 2021/22
BINYA PLACE | Project Planned |  | 0 | 381 | 380.53 | 110000 | 2021/22
BOBRA GLEN | Complete | 2021-08-16 | 0 | 119 | 118.71 | 30000 | 2021/22
BOONDOON CRESCENT | Project Planned |  | 0 | 214 | 214.15 | 57000 | 2021/22
CERON COURT | Project Planned |  | 0 | 83 | 82.59 | 30000 | 2021/22
COLLI CLOSE | Project Planned |  | 0 | 92 | 92.2 | 30000 | 2021/22
COONAWARRA COURT | Project Planned |  | 0 | 124 | 124.05 | 40000 | 2021/22
DANDALOO WAY | Complete | 2021-08-17 | 0 | 216 | 216.39 | 69000 | 2021/22
GAHWANG COURT | Project Planned |  | 0 | 125 | 128.14 | 41000 | 2021/22
GARA COURT | Project Planned |  | 0 | 76 | 75.56 | 25000 | 2021/22
GIBINGBELL CLOSE | Complete | 2021-08-18 | 0 | 136 | 135.61 | 45000 | 2021/22
INDERWONG AVENUE | Project Planned |  | 0 | 203 | 202.99 | 64000 | 2021/22
KANANDAH COURT | Project Planned |  | 0 | 144 | 144.42 | 46500 | 2021/22
KIAH CLOSE | Project Planned |  | 0 | 237 | 237.24 | 76500 | 2021/22
KIYUNG COURT | Project Planned |  | 0 | 173 | 172.97 | 56000 | 2021/22
MIRAM PLACE | Project Planned |  | 0 | 166 | 129.35 | 41500 | 2021/22
MURUMBA CLOSE | Project Planned |  | 0 | 226 | 225.85 | 72800 | 2021/22
NAMOI GLEN | Project Planned |  | 0 | 149 | 149.21 | 48000 | 2021/22
NARROGAL COURT | Project Underway |  | 0 | 169 | 168.96 | 54500 | 2021/22
NELSHABY COURT | Project Planned |  | 0 | 151 | 145.67 | 47000 | 2021/22
REDGATE ROAD | Project Planned |  | 0 | 914 | 914.21 | 275000 | 2021/22
REKA WAY | Complete | 2021-08-16 | 0 | 91 | 91.09 | 30000 | 2021/22
TATHRA GLEN | Project Planned |  | 0 | 179 | 179.42 | 58000 | 2021/22
THE ESPLANADE | Project Planned |  | 0 | 322 | 322.29 | 90500 | 2021/22
TINDARRA AVENUE | Complete | 2021-08-19 | 0 | 233 | 232.64 | 59000 | 2021/22
TONGARRA DRIVE | Project Planned |  | 480 | 600 | 126.06 | 38000 | 2021/22
TONGARRA DRIVE | Project Planned |  | 0 | 480 | 476.32 | 135000 | 2021/22
WALGOOAN WAY | Project Planned |  | 0 | 257 | 256.87 | 83000 | 2021/22
WARRAMBOOL ROAD | Project Planned |  | 5 | 772 | 766 | 310000 | 2021/22
WARRAMBOOL ROAD | Project Planned |  | 772 | 936 | 164.1 | 70500 | 2021/22
WATTAR COURT | Project Planned |  | 0 | 109 | 109.37 | 35500 | 2021/22
YUNGARUP PLACE | Project Planned |  | 0 | 252 | 252.47 | 81000 | 2021/22
ELIZABETH AVENUE | Project Planned |  |  |  |  | 90843.48 | 2021/22
GLORIA STREET | Project Planned |  |  |  |  | 138126.24 | 2021/22
GLORIA STREET | Project Planned |  |  |  |  | 24864 | 2021/22
HELEN STREET | Project Planned |  |  |  |  | 219030 | 2021/22
PACIFIC ESPLANADE | Project Planned |  |  |  |  | 94275.72 | 2021/22
PETER STREET | Project Planned |  |  |  |  | 137329.92 | 2021/22
ROBIN STREET | Project Planned |  |  |  |  | 137445.84 | 2021/22
ROYAL AVENUE | Project Planned |  |  |  |  | 91861.56 | 2021/22
ARIKA AVE | Project Planned | [5 empty] | 2021/22
YAMBLE DR | Project Planned | [5 empty] | 2021/22
ALCORN STREET | Project Planned |  |  |  |  | 64353.6 | 2021/22
CEMETERY ROAD | Project Planned |  |  |  |  | 238402.8 | 2021/22
McGREGOR STREET | Project Planned |  |  |  |  | 110619 | 2021/22
PATERSON STREET | Project Planned |  |  |  |  | 467235 | 2021/22
SHELLEY DRIVE | Project Planned |  |  |  |  | 358560 | 2021/22

## Reseals Program 1 year
Road | Locality | Status | Start | Finish | Length | Cost | Year
Fowlers Lane | Bangalow | Complete | 430 | 870 | 440 | 110000 | 2021/22
Mango Lane | Coorabell | Complete |  |  |  | 80000 | 2021/22
Middle Pocket Rd | Middle Pocket | Project Planned |  |  |  | 200000 | 2021/22

## Retaining Wall Program 1 year
Serial Number | Location | Status | Cost | Year
1 | 11 Bangalow Rd | Project Planned | 45000 | 2021/22
2 | Koranba Place / Coolamon Scenic Drive | Project Planned | 25000 | 2021/22
3 | Main Arm Rd / Murwillumbah Rd | Project Planned | 150000 | 2021/22

## Heavy Patching Program 1 year
Location | Status | Cost | Year
Bangalow Rd | Complete | 3000 | 2021/22
The Pocket Rd | Complete | 3500 | 2021/22
Ewingsdale Rd | Complete | 160000 | 2021/22
Sally Wattle Dr | Complete | 2038.82 | 2021/22
134 Coolamon Scenic Dr | Project Planned | 5000 | 2021/22
Coopers Shoot Rd | Project Planned | 5000 | 2021/22
Middle Pocket Rd | Project Planned | 200000 | 2021/22
ELIZABETH AVENUE |  |  |  | *Costs included in AC Overlay at the moment
GLORIA STREET
GLORIA STREET
HELEN STREET
PACIFIC ESPLANADE
PETER STREET
ROBIN STREET
ROYAL AVENUE
ARIKA AVE
YAMBLE DR
ALCORN STREET
CEMETERY ROAD
McGREGOR STREET
PATERSON STREET
SHELLEY DRIVE

## Footpath Program 1 year
Priority Number | Action | Street name | Status | Cost | Year
Column1 | Column2 | Column3 | Column4 | Column5 | Column6
20 | REPLACE SLAB | MAIN ARM ROAD | Project Planned | 5500 | 2021/22
34 | FILL | STUART STREET | Project Planned | 5000 | 2021/22
5 | FILL | DALLEY STREET | Project Planned | 4500 | 2021/22
26 |  | DALLEY STREET | Project Planned | 4500 | 2021/22
14 |  | STUART STREET | Project Planned | 5000 | 2021/22
29 | ROOT REMOVAL | STUART STREET | Project Planned | 22000 | 2021/22
40 | REPLACE SLAB | STUART STREET | Project Planned | 15000 | 2021/22
25 |  | BURRINGBAR STREET | Project Planned | 3500 | 2021/22
24 | GRIND | AZALEA STREET | Project Planned | 1500 | 2021/22
8 | REPLACE SLAB | LAWSON STREET | Project Planned | 2500 | 2021/22
38 |  | FLETCHER STREET | Project Planned | 3500 | 2021/22
37 |  | BAY STREET | Project Planned | 2500 | 2021/22
36 |  | BAY STREET | Project Planned | 2500 | 2021/22
7 | REPLACE SLAB | BYRON STREET | Project Planned | 3500 | 2021/22
28 | FILL | FLETCHER STREET | Project Planned | 3500 | 2021/22
6 |  | EWINGSDALE ROAD | Project Planned | 7500 | 2021/22
18 | REPLACE SLAB | SHIRLEY STREET | Project Planned | 5000 | 2021/22
33 |  | SHIRLEY STREET | Project Planned | 3500 | 2021/22
1 | FILL | SHIRLEY STREET | Project Planned | 3500 | 2021/22
11 |  | LILLI PILLI DRIVE | Project Planned | 4500 | 2021/22
21 |  | BROKEN HEAD ROAD | Project Planned | 4500 | 2021/22
19 | REPLACE SLAB | TAMARIND COURT | Project Planned | 2500 | 2021/22
15 |  | BOTTLEBRUSH CRESCENT | Project Planned | 2000 | 2021/22
2 | RESIDENCE LETTER | MANGO BARK COURT | Project Planned | 2500 | 2021/22
39 |  | PECAN COURT | Project Planned | 3500 | 2021/22
13 | AC PATCH | BROKEN HEAD ROAD | Project Planned | 3500 | 2021/22
23 | AC PATCH | EWINGSDALE ROAD | Project Planned | 7500 | 2021/22
9 |  | BYRON STREET | Project Planned | 2500 | 2021/22
32 |  | BYRON STREET | Project Planned | 3500 | 2021/22
35 |  | BOOYUN STREET | Project Planned | 4000 | 2021/22
31 | REPLACE SLAB | FINGAL STREET | Project Planned | 2500 | 2021/22
22 |  | FINGAL STREET | Project Planned | 3500 | 2021/22
4 |  | TWEED STREET | Project Planned | 2500 | 2021/22
3 |  | TWEED STREET | Project Planned | 3500 | 2021/22
30 |  | BOOYUN STREET | Project Planned | 3000 | 2021/22
17 |  | FINGAL STREET | Project Planned | 4500 | 2021/22
27 |  | MULLUMBIMBI STREET | Project Planned | 4500 | 2021/22
12 | GRIND | BRUNSWICK VALLEY WAY | Project Planned | 1500 | 2021/22
16 | CLEAN | BRUNSWICK VALLEY WAY | Project Planned | 2500 | 2021/22
10 | REPLACE SLAB | HELEN STREET | Project Planned | 3500 | 2021/22

## Kerb and Gutter Program 1 year
Location | Status | Cost | Year
SALLY WATTLE DR | Complete | 5500 | 2021/22
STUART ST | Complete | 15000 | 2021/22
43 FINGAL ST, BRUNSWICK HEADS | Project Planned | 3500 | 2021/22
4 RIFLE RANGE RD, BANGALOW | Project Planned | 2500 | 2021/22
LAWSON ST, BYRON BAY | Project Planned | 3000 | 2021/22
ALDINGA COURT | Project Planned | 2500 | 2021/22
BINYA PLACE | Complete | 5000 | 2021/22
BOBRA GLEN | Complete | 4500 | 2021/22
BOONDOON CRESCENT | Complete | 4500 | 2021/22
CERON COURT | Project Planned | 3500 | 2021/22
COLLI CLOSE | Complete | 3000 | 2021/22
COONAWARRA COURT | Complete | 5500 | 2021/22
DANDALOO WAY | Complete | 10500 | 2021/22
GIBINGBELL CLOSE | Complete | 6300 | 2021/22
INDERWONG AVENUE | Project Planned | 4500 | 2021/22
KANANDAH COURT | Project Planned | 4500 | 2021/22
KIAH CLOSE | Project Planned | 2500 | 2021/22
KIYUNG COURT | Project Planned | 2500 | 2021/22
MURUMBA CLOSE | Project Planned | 3500 | 2021/22
NAMOI GLEN | Project Planned | 6500 | 2021/22
NARROGAL COURT | Complete | 6500 | 2021/22
NELSHABY COURT | Project Planned | 5500 | 2021/22
REDGATE ROAD | Project Planned | 6500 | 2021/22
REKA WAY | Complete | 4500 | 2021/22
TATHRA GLEN | Complete | 3500 | 2021/22
THE ESPLANADE | Complete | 10500 | 2021/22
TINDARRA AVENUE | Complete | 9500 | 2021/22
TONGARRA DRIVE | Complete | 8500 | 2021/22
TONGARRA DRIVE | Complete | 8500 | 2021/22
WALGOOAN WAY | Project Planned | 1500 | 2021/22
WARRAMBOOL ROAD | Project Planned | 7500 | 2021/22
WARRAMBOOL ROAD | Project Planned | 8500 | 2021/22
WATTAR COURT | Project Planned | 6500 | 2021/22
YUNGARUP PLACE | Project Planned | 4500 | 2021/22

## Stormwater Program 1 year
Location | Details | Status | Cost | Year
Rajah Road | Pit lintel lifting. Kerb and gutter repairs. | Project Planned | 5000 | 2021/22
Ocean Shores Lintel repairs | Pit lintel lifting. Kerb and gutter repairs. | Project Planned | 25000 | 2021/22
The Strand kerb and gutter, swale | Kerb and gutter. Swale cut improvements | Project Planned | 7500 | 2021/22
Orana Road | Kerb and gutter renewals | Project Planned | 7500 | 2021/22
Brunswick St | Trash rack renewal | Project Planned | 5000 | 2021/22
Brunswick St outlet | Outlet pipe repairs | Project Planned | 25000 | 2021/22
SGB Outfall flood gates | Flood gates renewals and repairs | Project Planned | 25000 | 2021/22

## Access Ramps Program 1 year
Location | Details | Status | Cost | Year
Ocean Shores | 140m of footpath and 3 access ramps to connect Assisted Living Accomodation to Waterlilly Park. | Project Planned | 44000 | 2021/22

## Bridge Program 1 year
Location | Details | Status | Cost | Year
Tallow Creek Footbridge | Footpath approach improvements | Project Planned | 20000 | 2021/22
Orana Bridge, Ocean Shores | Replace bridge deck joints, restore steel balustrade | Project Planned | 65000 | 2021/23
Belongil Creek Bridge, Ewingsdale | Replace timber walkway decking, upgrade balustrade | Project Planned | 65000 | 2021/22